## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : PERSPEKTIV An Image Camouflaging Tool using Thayer Counter Shading
| DATE : |  | AMAR B P | KARTHIK M HOLIKATTI | CHETHAN S
MILESTONE 1 : REVISING C-PROGRAMMING CONCEPTS
| 2016-09-21 |  | Revising concepts of C programming | Revising concepts of C programming | Revising concepts of C programming
| 2016-09-22 |  | Revising concepts of C programming | Revising concepts of C programming | Revising concepts of C programming
| 2016-09-23 |  | Revising concepts of C programming | Revising concepts of C programming | Revising concepts of C programming
| 2016-09-24 |  | Tried to Learn MATLAB as an alternative language | Tried to Learn MATLAB as an alternative language | Tried to Learn MATLAB as an alternative language
| 2016-09-25 |  | SUNDAY
| 2016-09-26 |  | Unavailable | Unavailable | Unavailable
| 2016-09-27 |  | Unavailable | Unavailable | Unavailable
| 2016-09-28 |  | Understanding the breakdown of an image | Understanding the breakdown of an image | Understanding the breakdown of an image
2016-09-29
| 2016-09-30 |  | Download specific kind of images to check whether they are compatible with our parameters. | Download specific kind of images to check whether they are compatible with our parameters. | Download specific kind of images to check whether they are compatible with our parameters.
2016-10-01
| 2016-10-02 | INTERNALS
2016-10-03
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
| 2016-10-09 |  | SUNDAY | SUNDAY | SUNDAY
| 2016-10-10 | DASSERA HOLIDAYS
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16
| 2016-10-17 |  | Learning basics of MATLAB | Studying different JAVA packages | Checking the feasiblity of the project using JAVA
| 2016-10-18 |  | Learning basics of MATLAB | Studying different JAVA packages | Checking the feasiblity of the project using JAVA
| 2016-10-19 |  | Learning basics of MATLAB | Studying different JAVA packages | Checking the feasiblity of the project using JAVA
| 2016-10-20 |  | Learning basics of MATLAB | Studying different JAVA packages | Checking the feasiblity of the project using JAVA
| 2016-10-21 |  | Learning basics of MATLAB | Studying different JAVA packages | Checking the feasiblity of the project using MATLAB
| 2016-10-22 |  | Learning basics of MATLAB | Studying different JAVA packages | Checking the feasiblity of the project using MATLAB
| 2016-10-23 |  | Learning basics of MATLAB | Studying different JAVA packages | Checking the feasiblity of the project using MATLAB
| 2016-10-24 | TEAM MEETING WITH THE GUIDE TO Learn MORE ABOUT THE PROBLEM ASSOCIATED WITH THE PROJECT and PROJECT REVIEW
| 2016-10-25 |  | Learn how to extract CMYK values | Trying to extract the key value from CMYK | Studying about HISTOGRAM
| 2016-10-26 |  | Learn how to extract CMYK values | Trying to extract the key value from CMYK | Studying about HISTOGRAM
| 2016-10-27 |  | Learn how to extract CMYK values | Trying to extract the key value from CMYK | Studying about HISTOGRAM
| 2016-10-28 |  | Learn how to extract CMYK values | Trying to extract the key value from CMYK | Studying about HISTOGRAM
| 2016-10-29 | TEAM meeting and deciding on further topics
| 2016-10-30 | SUNDAY SUNDAY SUNDAY
| 2016-10-31 |  | VTU- SoftBall Tournament 2K16 at Don Bosco Institute Of Technology
2016-11-01
2016-11-02
2016-11-03
2016-11-04
| 2016-11-05 |  | Extracting CMYK values | Plotting of HISTOGRAM | Studying the extracted values from graph
| 2016-11-06 |  | SUNDAY
| 2016-11-07 |  | Extracting CMYK values | Plotting of HISTOGRAM | Studying the extracted values from graph
| 2016-11-08 |  | Extracting CMYK values | Plotting of HISTOGRAM | Studying the extracted values from graph
| 2016-11-09 |  | Extracting CMYK values | Plotting of HISTOGRAM | Studying the extracted values from graph
| 2016-11-10 |  | team meeting with the guide
| 2016-11-11 |  | Finding the average of the k values | Calculation of intensity of all the pixels in image | Replacing of all k values by k-avg value
| 2016-11-12 |  | Finding the average of the k values | Calculation of intensity of all the pixels in image | Replacing of all k values by k-avg value
| 2016-11-13 |  | 3rd-INTERNALS
2016-11-14
2016-11-15
2016-11-16
2016-11-17
2016-11-18
| 2016-11-19 |  | Finding the average of the k values | Calculation of intensity of all the pixels in image | Replacing of all k values by k-avg value
| 2016-11-20 |  | Finding the average of the k values | Calculation of intensity of all the pixels in image | Replacing of all k values by k-avg value
| 2016-11-21 |  | Finding the average of the k values | Calculation of intensity of all the pixels in image | Replacing of all k values by k-avg value
| 2016-11-22 |  | REPORTING THE UPDATES AND ALL THE VALUES TO THE GUIDE
| 2016-11-23 |  | Studying about the interface | Developing the code for CMYK extraction | Developing code for plotting histogram
| 2016-11-24 |  | Studying about the interface | Developing the code for CMYK extraction | Developing code for plotting histogram
| 2016-11-25 |  | Studying about the interface | Developing the code for CMYK extraction | Developing code for plotting histogram
| 2016-11-26 |  | Studying about the interface | Developing the code for CMYK extraction | Developing code for plotting histogram
| 2016-11-27 |  | SUNDAY
| 2016-11-28 |  | Externals
2016-11-29
2016-11-30
2016-12-01
2016-12-02
2016-12-03
2016-12-04
2016-12-05
2016-12-06
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-01
2017-01-02
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07
2017-01-08
| 2017-01-09 |  |  |  |  | Implementing SMS API in application
2017-01-10
2017-01-11
2017-01-12
2017-01-13
| 2017-01-14 |  | Milestone 2: Integration
2017-01-15
| 2017-01-16 |  | Work together on integrating all aspects of the software
2017-01-17
2017-01-18
2017-01-19
2017-01-20
2017-01-21
2017-01-22
2017-01-23
2017-01-24
2017-01-25